MMC Build MVP

Scoping & Deliverables by Build Stage

Optimised Architecture: Vercel + Supabase + Inngest

Prepared by Global Buildtech Australia Pty Ltd

ABN 54 672 395 685

For: MMC Build — Karen Van Den Engel, Founder & CEO

February 2026 | DRAFT v2.0

COMMERCIAL IN CONFIDENCE

# Executive Summary

This document defines the scoping, deliverables, and acceptance criteria for the MMC Build MVP, structured across eight build stages spanning approximately 18 weeks.

This version proposes an optimised technology stack (Vercel + Supabase + Inngest) that replaces the FastAPI + AWS infrastructure specified in PRD v3.0 Section 4. This alternative delivers every functional requirement in the PRD while reducing complexity, cost, timeline, and potential failure points.

Why the Architecture Change:

- Eliminates 4–6 weeks of infrastructure provisioning (no Terraform, no ECS/Fargate, no Docker containers, no VPC configuration)

- Reduces managed services from ~10 to ~4 (fewer failure points, simpler monitoring)

- Lowers running costs from $300–500+/month to ~$75–150/month at MVP scale

- Single language (TypeScript) across frontend and backend (eliminates Python/FastAPI codebase)

- Zero vendor lock-in — Next.js is open source, Supabase is open-source PostgreSQL. Full migration path to AWS preserved for enterprise phase.

- AU data residency maintained — Supabase Sydney region, Vercel Edge Network serves from Sydney.

- R&D Tax Rebate eligibility unaffected — qualifying criteria relate to developer ABN/location, not hosting platform.

The eight build stages are:

| Stage | Name | Duration | R&D Eligible | Key Output |
| --- | --- | --- | --- | --- |
| 0 | Project Setup & Foundation | Weeks 1–2 | Partial | Infra + Auth + CI/CD |
| 1 | MMC Comply — NCC Compliance Engine | Weeks 3–8 | Core R&D | NCC Compliance Reports |
| 2 | MMC Build — Design Optimisation | Weeks 7–11 | Core R&D | Design Optimisation Reports |
| 3 | MMC Quote — Cost Estimation | Weeks 10–12 | Core R&D | Cost Estimates |
| 4 | MMC Direct — Trade Directory | Weeks 11–13 | Not Eligible | Trade Directory |
| 5 | MMC Train — Training Modules | Weeks 12–14 | Not Eligible | Training Modules |
| 6 | Billing, Observability & Launch | Weeks 13–16 | Partial | Billing + Observability |
| 7 | Pilot, Iteration & Handover | Weeks 16–18 | Partial | Pilot Launch + Handover |

# Technology Stack — PRD Mapping

The following table maps each PRD architecture requirement to the proposed implementation. Every functional capability is preserved; only the infrastructure delivery mechanism changes.

| PRD Requirement | PRD v3.0 Spec (AWS/FastAPI) | Proposed (Vercel/Supabase) | Notes |
| --- | --- | --- | --- |
| Frontend | Next.js (React + TypeScript) | Next.js on Vercel | No change — Vercel is purpose-built for Next.js |
| Backend API | Python FastAPI on ECS/Fargate | Next.js Server Actions + API Routes | Eliminates separate backend server entirely |
| Database | AWS RDS PostgreSQL | Supabase PostgreSQL (Sydney) | Same engine, managed, built-in dashboard |
| Vector Search | pgvector + OpenSearch | pgvector on Supabase | OpenSearch eliminated; pgvector + full-text search sufficient for MVP |
| Auth & RBAC | Custom JWT + middleware | Supabase Auth + Row-Level Security | Built-in, less code, battle-tested |
| File Storage | AWS S3 | Supabase Storage (S3-backed) | Same underlying storage, simpler API |
| Cache | AWS ElastiCache (Redis) | Vercel KV (optional) | Redis eliminated for MVP; add if needed |
| Job Queue | AWS SQS + Celery workers | Inngest durable functions | Serverless, built-in retries, step functions |
| Event Bus | AWS EventBridge | Supabase Realtime + Inngest events | Simpler, no separate service |
| IaC | Terraform (VPC, subnets, ECS, etc.) | Supabase CLI migrations + Vercel | Weeks of Terraform work eliminated |
| Containers | Docker + ECS/Fargate | None (serverless) | No container management |
| Observability | CloudWatch + OpenTelemetry + Grafana | Vercel Analytics + Sentry + Supabase logs | Simpler, sufficient for MVP |
| CI/CD | GitHub Actions → Docker → ECS | GitHub Actions → Vercel auto-deploy | Simpler pipeline, PR preview deploys free |
| Data Residency | AWS Sydney (ap-southeast-2) | Supabase Sydney + Vercel Edge Sydney | AU residency maintained |
| Payments | Stripe via FastAPI | Stripe via Next.js API routes | No change in approach |

# Monthly Cost Comparison (MVP Scale)

Running cost comparison at MVP scale (5–10 pilot firms, low-to-moderate traffic):

| Service | AWS/FastAPI Stack | Vercel/Supabase Stack |
| --- | --- | --- |
| Compute (API + workers) | $150–250/mo (ECS/Fargate) | $20/mo (Vercel Pro) |
| Database | $50–100/mo (RDS) | $25/mo (Supabase Pro) |
| Cache | $30–50/mo (ElastiCache) | $0–5/mo (Vercel KV, optional) |
| Search | $50–100/mo (OpenSearch) | $0 (pgvector included) |
| File Storage | $5–10/mo (S3) | $0 (included in Supabase Pro) |
| Queue/Events | $10–20/mo (SQS + EventBridge) | $0 (Inngest free tier) |
| Monitoring | $20–40/mo (CloudWatch) | $0 (Vercel Analytics + Sentry free) |
| Total Infrastructure | $315–570/month | $45–50/month |
| LLM API costs (OpenAI/Anthropic) | $50–200/mo | $50–200/mo (same) |
| Total | $365–770/month | $95–250/month |

Note: LLM API costs are usage-based and identical regardless of architecture choice. The infrastructure savings of $270–520/month are recurring and compound over the pilot period.

# Stage 0: Project Setup & Foundation

Duration: Weeks 1–2  |  R&D Eligibility: Partial

Establish the development environment, CI/CD pipeline, Supabase project, database schema, authentication, and base application scaffolding. With the Vercel + Supabase stack, this stage is significantly faster than the AWS equivalent — no Terraform, no VPC, no container configuration.

| Deliverable | Description |
| --- | --- |
| Supabase project (Sydney region) | Database provisioned with pgvector extension, Auth configured, Storage buckets created, Row-Level Security policies for multi-tenancy |
| Vercel project + CI/CD | Next.js app deployed to Vercel, GitHub integration for auto-deploy, PR preview environments enabled |
| Database schema v1 | All migrations: tenants, users, roles, projects, plans, reports, feedback, audit_log. RLS policies enforced. |
| Authentication & RBAC | Supabase Auth: email + OAuth signup/login, JWT tokens, role definitions (Owner, Admin, Member, Viewer), invitation flow |
| Application scaffolding | Next.js App Router structure, Tailwind + shadcn/ui component library, typed Supabase client, server actions pattern |
| Inngest integration | Inngest client connected, webhook endpoint configured, first test function deployed |
| R&D documentation setup | Experiment log template, hypothesis register, timesheet tracking categories aligned to R&D activity codes |

Acceptance Criteria:

- Staging environment accessible and auto-deploying from Git

- Auth flow working: signup, login, invite, role assignment

- Database migrations run cleanly with tenant isolation verified via RLS

- Inngest function executes successfully from API route trigger

Estimated Effort: ~7 days (vs ~13 days on AWS stack)

# Stage 1: MMC Comply — NCC Compliance Engine

Duration: Weeks 3–8  |  R&D Eligibility: Core R&D

The primary R&D workstream. Build the AI-powered compliance checking engine that analyses uploaded building plans against the National Construction Code (NCC). This is the technical centrepiece of the MVP and the strongest R&D Tax Incentive claim area.

| Deliverable | Description | R&D Tag | Est. Effort |
| --- | --- | --- | --- |
| Plan upload interface | Drag-and-drop upload with validation (PDF, DWG). Files stored in Supabase Storage with metadata in PostgreSQL. | — | 2 days |
| Document processing pipeline (Inngest) | PDF text extraction, page segmentation, OCR for scanned plans. Multi-step Inngest function with status updates via Supabase Realtime. | — | 3 days |
| NCC knowledge base | NCC Volume 1 & 2 ingestion, chunking, embedding pipeline. pgvector storage with metadata tagging (section, clause, amendment date). Benchmark dataset of 50+ compliance scenarios. | R&D Core | 5 days |
| Embedding pipeline | Generate and store vector embeddings via OpenAI ada-002. pgvector similarity search + Supabase full-text search for hybrid retrieval. | R&D Core | 4 days |
| RAG pipeline | Parse → Embed → Query NCC → Generate assessment → Cite sources. Central orchestrator with model routing (GPT-4 / Claude). | R&D Core | 5 days |
| Guided questionnaire engine | Dynamic form: building class, climate zone, site conditions, intended use. Responses passed to AI context. | — | 3 days |
| AI compliance analysis engine | Multi-pass analysis: structural, fire safety, accessibility, energy, weatherproofing. Confidence scoring, low-confidence flagging (≤70%). | R&D Core | 5 days |
| Compliance report generation | PDF report: executive summary, clause-by-clause findings, risk flags, citations, confidence. Side panel UI with NCC references. | — | 3 days |
| Feedback & correction interface | Thumbs up/down per finding, free-text corrections, stored for retraining pipeline. | — | 2 days |
| Prompt engineering & model routing | Model selection logic, A/B test framework for prompt variants, experiment documentation. | R&D Core | 3 days |
| R&D Experiment: Precision benchmarking | Benchmark dataset, baseline metrics, ≥90% precision target tested and documented. | R&D Core | 3 days |

Acceptance Criteria:

- End-to-end: upload plan → complete questionnaire → receive compliance report

- AI compliance precision ≥85% against benchmark dataset (target 90% by pilot)

- Processing time <2 minutes per plan (Inngest pipeline)

- NCC citations traceable to specific clauses in every finding

Estimated Effort: ~38 days | R&D Eligible: ~25 days

# Stage 2: MMC Build — Design Optimisation

Duration: Weeks 7–11 (overlaps Stage 1)  |  R&D Eligibility: Core R&D

Build the AI-assisted design optimisation module that suggests modifications using MMC methods (prefabrication, SIP systems, panelised construction). Extends the RAG pipeline from Stage 1.

| Deliverable | Description | R&D Tag | Est. Effort |
| --- | --- | --- | --- |
| MMC methods knowledge base | Curated dataset: prefab, SIPs, CLT, panelised, modular, hybrid. Supplier specs embedded for RAG retrieval. | R&D Core | 4 days |
| Design analysis engine | AI pipeline analysing plans for MMC opportunities. Structured output: suggestion, rationale, estimated impact. | R&D Core | 5 days |
| Original vs Optimised comparison | Side-by-side or overlay view with annotation layer. Summary panel with aggregate improvement metrics. | — | 4 days |
| Design optimisation report | PDF: optimisation summary, recommendations, estimated savings, MMC method references. | — | 2 days |
| R&D Experiment: Accuracy vs expert review | Blind comparison on 5+ plans, results documented for R&D report. | R&D Core | 3 days |

Estimated Effort: ~18 days | R&D Eligible: ~12 days

# Stage 3: MMC Quote — Cost Estimation

Duration: Weeks 10–12 (overlaps Stage 2)  |  R&D Eligibility: Core R&D

| Deliverable | Description | R&D Tag | Est. Effort |
| --- | --- | --- | --- |
| Supplier price list knowledge base | Ingestion pipeline for catalogues (PDF, CSV, XLSX). Structured extraction, embedding, indexing. | R&D Core | 3 days |
| Cost estimation engine | AI pipeline: map plan elements to materials, retrieve pricing, calculate estimates with confidence bands. | R&D Core | 5 days |
| Interactive quote builder | Line items, quantities, costs. User can adjust/swap/override. Summary with confidence band. | — | 3 days |
| Quote report export | PDF + XLSX: itemised quote, supplier references, assumptions. | — | 2 days |

Estimated Effort: ~13 days | R&D Eligible: ~8 days

# Stage 4: MMC Direct — Trade & Consultant Directory

Duration: Weeks 11–13  |  R&D Eligibility: Not Eligible

| Deliverable | Description | Est. Effort |
| --- | --- | --- |
| Directory data model | Schema: companies, professionals, certifications, ABN, regions, specialisations, ratings. Seed data. | 2 days |
| Profile pages | Company/professional profile: ABN, licences, certifications, service areas, compliance score. | 2 days |
| Search & filtering | Category browsing + multi-filter: location, specialty, certification, rating. Supabase full-text search. | 3 days |
| Shortlist & contact | Shortlist per project, send invitation/contact request from profile. | 1 day |

Estimated Effort: ~8 days | R&D Eligible: 0 days

# Stage 5: MMC Train — Training Modules

Duration: Weeks 12–14  |  R&D Eligibility: Not Eligible

| Deliverable | Description | Est. Effort |
| --- | --- | --- |
| Course CMS | Schema: courses, modules, lessons, quizzes, enrolments. Admin interface for content management. | 3 days |
| Learner interface | Course catalogue, module player, sequential progression, quiz engine with scoring. | 2 days |
| Progress & certificates | Per-user dashboard, completion tracking, auto-generated PDF certificates via Inngest. | 2 days |

Estimated Effort: ~7 days | R&D Eligible: 0 days

# Stage 6: Billing, Observability & Launch Readiness

Duration: Weeks 13–16  |  R&D Eligibility: Partial

| Deliverable | Description | R&D Tag | Est. Effort |
| --- | --- | --- | --- |
| Stripe billing integration | Test mode: subscription plans, checkout, customer portal. 60-day free trial → paid. Webhooks via Next.js API route. | — | 3 days |
| Observability | Vercel Analytics + Sentry: error tracking, performance monitoring. Supabase dashboard for DB metrics. | — | 2 days |
| AI model observability | Benchmark regression suite, drift monitoring, feedback loop pipeline, experiment dashboard. | R&D Supporting | 2 days |
| Security hardening | TLS enforced, Supabase RLS audit, RBAC endpoint verification, audit trail review. | — | 2 days |
| End-to-end testing | Integration + UAT test suite. All core workflows pass. | — | 4 days |
| Pilot launch package | Invite-only onboarding, in-app feedback prompts, welcome emails, support channel. | — | 2 days |
| R&D evidence pack | Experiment logs, hypothesis outcomes, timesheet summaries, commit evidence. Draft for AusIndustry. | R&D Supporting | 2 days |

Estimated Effort: ~17 days | R&D Eligible: ~4 days

# Stage 7: Pilot, Iteration & Handover

Duration: Weeks 16–18  |  R&D Eligibility: Partial

| Deliverable | Description | R&D Tag | Est. Effort |
| --- | --- | --- | --- |
| Pilot onboarding | Onboard 5–10 firms. Guided walkthroughs of Comply, Build, and Quote. | — | 3 days |
| Feedback analysis & iteration | Weekly feedback review. Prioritised bug fixes and UX improvements. | — | 4 days |
| AI retraining cycle | Incorporate corrections into training data. Re-run benchmarks. Document outcomes. | R&D Supporting | 3 days |
| Post-pilot survey | Structured survey: usability, accuracy, perceived value, willingness to pay. | — | 1 day |
| Handover documentation | Architecture docs, deployment runbooks, API reference, operational playbook, product backlog. | — | 3 days |
| Final R&D report | Complete experiment report for AusIndustry. Evidence pack finalised. | R&D Supporting | 2 days |

Estimated Effort: ~16 days | R&D Eligible: ~5 days

# Summary: Effort by Stage

| Stage | Weeks | Total Days | R&D Days | R&D % |
| --- | --- | --- | --- | --- |
| Stage 0: Project Setup & Foundation | 1–2 | 7 | 1 | 14% |
| Stage 1: MMC Comply (NCC Compliance) | 3–8 | 38 | 25 | 66% |
| Stage 2: MMC Build (Design Optimisation) | 7–11 | 18 | 12 | 67% |
| Stage 3: MMC Quote (Cost Estimation) | 10–12 | 13 | 8 | 62% |
| Stage 4: MMC Direct (Trade Directory) | 11–13 | 8 | 0 | 0% |
| Stage 5: MMC Train (Training Modules) | 12–14 | 7 | 0 | 0% |
| Stage 6: Billing, Observability & Launch | 13–16 | 17 | 4 | 24% |
| Stage 7: Pilot, Iteration & Handover | 16–18 | 16 | 5 | 31% |
| TOTAL | 18 weeks | 124 days | 55 days | 44% |

The Vercel + Supabase stack saves approximately 24 days (~4.8 weeks) compared to the AWS/FastAPI version (148 days → 124 days), primarily by eliminating infrastructure provisioning and container management work.

Of the 124 estimated days, approximately 55 days (44%) are R&D-eligible activities that would support an R&D Tax Incentive claim under AusIndustry guidelines.

# Scalability & Migration Path

The Vercel + Supabase stack comfortably supports the MVP and early growth phases. The following table identifies when specific enterprise triggers would justify migrating individual components to AWS:

| Trigger | Component to Migrate | When | Estimated Effort |
| --- | --- | --- | --- |
| Enterprise client requires private VPC | Compute → AWS ECS/Fargate | Post-MVP, customer-funded | 2–3 weeks |
| AI pipelines exceed 5min / need GPU | AI workers → AWS Lambda/ECS | Scale phase | 1–2 weeks |
| 10,000+ concurrent users | Database → AWS RDS with read replicas | Significant scale | 1 week |
| Enterprise SSO/SAML requirements | Auth → Auth0 or AWS Cognito | Enterprise contracts | 1 week |
| Regulatory audit requires full AWS | Full migration | Enterprise compliance | 4–6 weeks |

Key point: these migrations are incremental, not all-or-nothing. The open-source foundation (Next.js, PostgreSQL) means each component can be migrated independently when a specific business trigger justifies it.

# Dependencies & Assumptions

## Client-Provided Dependencies

| Dependency | Owner | Impact if Delayed |
| --- | --- | --- |
| NCC Volume 1 & 2 content (licensed) | MMC Build | Blocks Stage 1 entirely |
| Supplier price lists and specifications | MMC Build | Blocks MMC Quote in Stage 3 |
| Sample building plans (PDF) for testing | MMC Build | Degrades AI accuracy testing |
| Training course content | MMC Build | Blocks MMC Train in Stage 5 |
| Directory seed data (verified trades) | MMC Build | Directory launches empty |
| 5–10 pilot firms confirmed | MMC Build | Blocks Stage 7 |
| Stripe account (test mode) | MMC Build | Blocks billing in Stage 6 |
| Domain, DNS, SSL | MMC Build | Blocks production deployment |
| UX/UI designs (Figma) | MMC Build or GBTA | GBTA provides functional UI if not supplied |
| Feedback/approvals at stage gates | MMC Build | ≤5 business days per gate |

## Technical Assumptions

- Single full-stack developer (GBTA) delivering all stages

- Supabase Pro plan with Sydney (ap-southeast-2) region for AU data residency

- Vercel Pro plan for production hosting and serverless functions

- TypeScript (Next.js) for all frontend and backend code — no Python/FastAPI

- OpenAI API (GPT-4 Turbo) as primary LLM; Anthropic Claude as fallback/comparison

- Inngest for async AI pipeline orchestration (replaces SQS/Celery)

- pgvector on Supabase for embeddings (no separate vector DB or OpenSearch)

- 3D viewer is a stretch goal; may be descoped to 2D overlay

- AI model costs (OpenAI/Anthropic) billed separately or passed through

- R&D documentation maintained contemporaneously throughout the build

- Estimates assume no scope changes; change requests managed via agreed process

## R&D Tax Incentive

- All development performed by Australian-resident developers under GBTA (ABN 54 672 395 685)

- Timesheets tracked against R&D activity categories from project commencement

- MMC Build Pty Ltd is the R&D entity and claimant; GBTA is the contracted service provider

- Architecture choice (Vercel/Supabase vs AWS) does not affect R&D eligibility

# Key Risks

| Risk | Impact | Mitigation |
| --- | --- | --- |
| NCC content licensing | Without licensed NCC access, compliance engine cannot be built. Blocks Stage 1. | Client to confirm access before Stage 1 |
| AI accuracy below target | Precision below 90% undermines trust and PMF. | Iterative prompt engineering; human-in-the-loop; extended pilot tuning |
| 3D viewer complexity | Full 3D from 2D plans is ambitious for MVP. | Descope to 2D annotated overlay; defer full 3D to Phase 2 |
| Supplier data quality | Inconsistent price lists reduce quoting accuracy. | Structured ingestion with validation; confidence bands on estimates |
| Vercel function timeout | AI pipelines exceeding 60s on Vercel Pro. | Inngest handles long-running pipelines outside Vercel timeout limits |
| Scope creep (6 modules) | Ambitious module count risks diluted quality. | Stage gates with go/no-go; prioritise Comply as wedge product |
| R&D claim rejection | Inadequate documentation risks ATO rejection. | Contemporaneous documentation; R&D advisor review before submission |

# Next Steps

- Confirm architecture approach (Vercel + Supabase vs AWS/FastAPI)

- Confirm NCC content licensing pathway and access timeline

- Confirm supplier price list data availability and format

- Finalise pricing model based on this scoping (fixed price per stage vs time & materials)

- Agree stage gate review process and approval cadence

- Prepare formal quotation based on agreed scope